## Sheet1
TCOF Success Factor | 1 Identification | 2 Definition | 3 Delivery | 4 Closure
1.1 Ask Why | Consult key stakeholders | - | - | -
1.1 Ask Why | Understand pains and wants | - | - | -
1.1 Ask Why | Define goals | - | - | -
1.2 Get a Masterbuilder | Define the type of person you need | Confirm you have access to a master builder ready for the next stage | Confirm you have access to a master builder ready for the next stage | -
1.2 Get a Masterbuilder | Find a leader | - | - | -
1.2 Get a Masterbuilder | Get access to additional support (if needed) | - | - | -
1.3 Get Your People on the Bus | Get a team that has worked with your masterbuilder (if possible) | Build support with Change Champions | Support champions to influence others | -
1.3 Get Your People on the Bus | Identify early champions (if there is business change) | Enable team productivity | Enable team productivity | -
1.3 Get Your People on the Bus | Run team development workshops | - | - | -
1.4 Make Friends and Keep them Friendly | Create a plan to engage with other stakeholders | Stakeholder communications, training and engagement | Stakeholder communications, training and engagement | -
1.4 Make Friends and Keep them Friendly | Engage stakeholders, customers, and users | Empower stakeholders, users, customers to support decision making | Empower stakeholders, users, customers to support decision making | -
1.4 Make Friends and Keep them Friendly | Develop a mechanism to foster transparency and involve stakeholders in key decisions | - | - | -
2.1 Recognise that your project is not unique | Identify and learn lessons from three people or projects that have achieved similar outcomes | Re-engage with past projects to learn new lessons about the next stage | - | -
2.1 Recognise that your project is not unique | Find out how long their projects took, what they cost, and whether the expected value was delivered | - | - | -
2.1 Recognise that your project is not unique | Apply these insights to your plan | - | - | -
2.2 Look for Tried & Tested Options | Identify three delivery methods using tried and tested techniques | - | - | -
2.2 Look for Tried & Tested Options | Validate your best option through prototyping and customer or user feedback | - | - | -
2.2 Look for Tried & Tested Options | Complete a pros and cons list for each option. Rate against: - Use of tried and tested methods - Likelihood of delivering goals - Modularity and scalability - Ease of building a minimum or maximum viable product Include metrics where possible | - | - | -
3.1 Think Big, Start Small | Break your preferred solution into small, modular parts | Re-engage with past projects to learn new lessons about the next stage | Scale up and go big. Roll out sections / modular solution to other areas | -
3.1 Think Big, Start Small | Ask the question: what is my Lego? | Validate that the solution will achieve the goals. | - | -
3.1 Think Big, Start Small | Ensure people and plans are in place to develop the solution in Phase 2 | - | - | -
3.2 Learn by Experimenting | Create a plan to develop an MVP or MXVP in Stage 2 | Develop module as a minimum viable product, if possible. Otherwise, develop a maximum virtual product. | Continue regular learning and reflection sessions (at least monthly) | -
3.2 Learn by Experimenting | Start regular reflection sessions: weekly, fortnightly, or monthly | Continue regular learning and reflection sessions (at least monthly) | - | -
3.3 Keep on top of risks | List your top five risks now | Continuously identify and mittigate risks (review at least monthly) | Continuously identify and mitigate risks (review at least monthly) | -
3.3 Keep on top of risks | Create a mitigation plan for each one | - | - | -
3.3 Keep on top of risks | Review and update your risk plan monthly (or more often) | - | - | -
4.1 Adjust for optimism | Compare how long similar projects took in Stage 2 and 3 versus their original estimates | Look to previous projects to identify level of optimism for Stage 3, apply this contingency % to your estimate for time / cost / resources required for stage 3 | Build optimism allowances into all forecasts. | -
4.1 Adjust for optimism | Adjust your forecast based on this optimism allowance and include contingency | - | - | -
4.2 Measure What Matters, Be Ready to Step Away | Identify the success measures for your solution in Stage 2 | Identify the measurable success measures for your solution in Stage 3 | Confirm the built solution meets your goals. Measure this with metrics. | Record results for posterity
4.2 Measure What Matters, Be Ready to Step Away | Confirm the business case do the benefits outweigh the costs? | Confirm the business case do the benefits outweigh the costs? | - | -
4.2 Measure What Matters, Be Ready to Step Away | - | Confirm you've used data to validate your chosen option and plan, including optimism bias | - | -
4.3 Be Ready to Adapt | Set up regular meetings with key people to adapt to a changing world | Adapt the requirements / plan / scope based as new information comes to light. | Adapt the requirements / plan / scope based as new information comes to light. | -