## Stage_1_4_Task_Breakdown
Stage | SF ID | Success Factor | Task
Stage 1 | 1.1 | Ask Why | Talk to 3 to 5 key stakeholders
Stage 1 | 1.1 | Ask Why | Ask what frustrates them and what a win looks like
Stage 1 | 1.1 | Ask Why | Draft a clear purpose statement, refine the goals, update the Success Map
Stage 1 | 1.2 | Get a Masterbuilder | Define the type of person you need
Stage 1 | 1.2 | Get a Masterbuilder | Find a leader
Stage 1 | 1.2 | Get a Masterbuilder | Get access to additional support (if needed)
Stage 2 | 1.2 | Get a Masterbuilder | Confirm you have access to a master builder ready for the next stage
Stage 1 | 1.3 | Get your People on the Bus | Get a team that has worked with your masterbuilder (if possible)
Stage 1 | 1.3 | Get your People on the Bus | Identify early champions (if there is business change)
Stage 1 | 1.3 | Get your People on the Bus | Run team development workshops
Stage 2 | 1.3 | Get your People on the Bus | Build support with Change Champions
Stage 2 | 1.3 | Get your People on the Bus | Get Your People on the Bus: Build team productivity
Stage 3 | 1.3 | Get your People on the Bus | Support champions to influence others
Stage 3 | 1.3 | Get your People on the Bus | Setup the team to be productive
Stage 1 | 1.4 | Make Friends and Keep them Friendly | Create a plan to engage with other stakeholders
Stage 1 | 1.4 | Make Friends and Keep them Friendly | Engage stakeholders, customers, and users
Stage 1 | 1.4 | Make Friends and Keep them Friendly | Develop a mechanism to foster transparency and involve stakeholders in key decisions
Stage 2 | 1.4 | Make Friends and Keep them Friendly | Stakeholder communications, training and engagement
Stage 2 | 1.4 | Make Friends and Keep them Friendly | Empower stakeholders, users, customers to support decision making
Stage 3 | 1.4 | Make Friends and Keep them Friendly | Stakeholder communications, training and engagement
Stage 3 | 1.4 | Make Friends and Keep them Friendly | Empower stakeholders, users, customers to support decision making
Stage 1 | 2.1 | Recognise Your Project Is Not Unique | Identify and learn lessons from three people or projects that have achieved similar outcomes
Stage 1 | 2.1 | Recognise Your Project Is Not Unique | Find out how long their projects took, what they cost, and whether the expected value was delivered
Stage 1 | 2.1 | Recognise Your Project Is Not Unique | Apply these insights to your plan
Stage 2 | 2.1 | Recognise Your Project Is Not Unique | Reengage with past projects to learn new lessons about the next stage
Stage 1 | 2.2 | Look for Tried & Tested Options | Identify three delivery methods using tried and tested techniques
Stage 1 | 2.2 | Look for Tried & Tested Options | Validate your best option through prototyping and customer or user feedback
Stage 1 | 2.2 | Look for Tried & Tested Options | Complete a pros and cons list for each option. Rate against: Use of tried and tested methods, Likelihood of delivering goals, Modularity and scalability, Ease of building a minimum or maximum viable product. Include metrics where possible.
Stage 1 | 3.1 | Think Big, Start Small | Answer the question: what is my Lego?
Stage 1 | 3.1 | Think Big, Start Small | Ensure people and plans are in place to develop the solution in stage 2
Stage 2 | 3.1 | Think Big, Start Small | Develop module as a minimum viable product, if possible. Otherwise, develop a maximum virtual product.
Stage 3 | 3.1 | Think Big, Start Small | Scale up and go big. Roll out sections / modular solution to other areas
Stage 2 | 3.1 | Think Big, Start Small | Validate that the solution will achieve the goals.
Stage 1 | 3.2 | Learn by Experimenting | Generate experiential learning to test key assumptions
Stage 1 | 3.2 | Learn by Experimenting | Start regular reflection sessions: weekly, fortnightly, or monthly
Stage 1 | 3.2 | Learn by Experimenting | Create a plan to develop an minimum viable product, or where this isnâ€™t possible, a maximum virtual product in in Stage 2
Stage 2 | 3.2 | Learn by Experimenting | Develop module as a minimum viable product, if possible. Otherwise, develop a maximum virtual product.
Stage 2 | 3.2 | Learn by Experimenting | Continue regular learning and reflection sessions (at least monthly)
Stage 3 | 3.2 | Learn by Experimenting | Continue regular learning and reflection sessions (at least monthly)
Stage 1 | 3.3 | Keep On Top of Risks | List your top five risks now
Stage 1 | 3.3 | Keep On Top of Risks | Create a mitigation plan for each one
Stage 1 | 3.3 | Keep On Top of Risks | Review and update your risk plan monthly (or more often).
Stage 2 | 3.3 | Keep On Top of Risks | Continuously identify and mitigate risks (at least monthly)
Stage 3 | 3.3 | Keep On Top of Risks | Continuously identify and mitigate risks (at least monthly)
Stage 1 | 4.1 | Adjust for Optimism | Compare how long similar projects took in Stage 2 and 3 versus their original estimates
Stage 1 | 4.1 | Adjust for Optimism | Adjust your forecast based on this optimism allowance and include contingency
Stage 2 | 4.1 | Adjust for Optimism | Look to previous projects to identify level of optimism for Stage 3, apply this contingency % to your estimate for time / cost / resources required for stage 3
Stage 3 | 4.1 | Adjust for Optimism | Build optimism allowances into all forecasts, big and small.
Stage 1 | 4.2 | Measure What Matters, Be Ready to Step Away | Identify the success measures for your solution in Stage 2
Stage 1 | 4.2 | Measure What Matters, Be Ready to Step Away | Confirm the business case do the benefits outweigh the costs?
Stage 2 | 4.2 | Measure What Matters, Be Ready to Step Away | Identify the measurable success measures for your solution in Stage 3
Stage 2 | 4.2 | Measure What Matters, Be Ready to Step Away | Confirm the business case do the benefits outweigh the costs?
Stage 2 | 4.2 | Measure What Matters, Be Ready to Step Away | Confirm you've used data to validate your chosen option and plan, including optimism bias
Stage 3 | 4.2 | Measure What Matters, Be Ready to Step Away | Confirm the built solution meets your goals. Measure this with metrics.
Stage 4 | 4.2 | Measure What Matters, Be Ready to Step Away | Record results for posterity
Stage 4 | 4.2 | Measure What Matters, Be Ready to Step Away | Capture and share learning, insights and successful heuristics
Stage 1 | 4.3 | Be Ready to Adapt | Set up regular meetings with key people to adapt to a changing world
Stage 2 | 4.3 | Be Ready to Adapt | Adapt the requirements / plan / scope based as new information comes to light.
Stage 3 | 4.3 | Be Ready to Adapt | Adapt the requirements / plan / scope based as new information comes to light.