## Sheet1
Category | TCOF Success Factor | Your Heuristic / Title | 1 Identification | 2 Definition | 3 Delivery | 4 Closure
1. TCOF Success Factors | 1.1 Ask Why |  | Consult key stakeholders | - | - | -
1. TCOF Success Factors | 1.1 Ask Why |  | Understand pains and wants | - | - | -
1. TCOF Success Factors | 1.1 Ask Why |  | Define goals | - | - | -
1. TCOF Success Factors | 1.2 Get a Masterbuilder |  | Define the type of person you need | Confirm you have access to a master builder ready for the next stage | Confirm you have access to a master builder ready for the next stage | -
1. TCOF Success Factors | 1.2 Get a Masterbuilder |  | Find a leader | - | - | -
1. TCOF Success Factors | 1.2 Get a Masterbuilder |  | Get access to additional support (if needed) | - | - | -
1. TCOF Success Factors | 1.3 Get Your People on the Bus |  | Get a team that has worked with your masterbuilder (if possible) | Build support with Change Champions | Support champions to influence others | -
1. TCOF Success Factors | 1.3 Get Your People on the Bus |  | Identify early champions (if there is business change) | Enable team productivity | Enable team productivity | -
1. TCOF Success Factors | 1.3 Get Your People on the Bus |  | Run team development workshops | - | - | -
1. TCOF Success Factors | 1.4 Make Friends and Keep them Friendly |  | Create a plan to engage with other stakeholders | Stakeholder communications, training and engagement | Stakeholder communications, training and engagement | -
1. TCOF Success Factors | 1.4 Make Friends and Keep them Friendly |  | Engage stakeholders, customers, and users | Empower stakeholders, users, customers to support decision making | Empower stakeholders, users, customers to support decision making | -
1. TCOF Success Factors | 1.4 Make Friends and Keep them Friendly |  | Develop a mechanism to foster transparency and involve stakeholders in key decisions | - | - | -
1. TCOF Success Factors | 2.1 Recognise that your project is not unique |  | Identify and learn lessons from three people or projects that have achieved similar outcomes | Re-engage with past projects to learn new lessons about the next stage | - | -
1. TCOF Success Factors | 2.1 Recognise that your project is not unique |  | Find out how long their projects took, what they cost, and whether the expected value was delivered | - | - | -
1. TCOF Success Factors | 2.1 Recognise that your project is not unique |  | Apply these insights to your plan | - | - | -
1. TCOF Success Factors | 2.2 Look for Tried & Tested Options |  | Identify three delivery methods using tried and tested techniques | - | - | -
1. TCOF Success Factors | 2.2 Look for Tried & Tested Options |  | Validate your best option through prototyping and customer or user feedback | - | - | -
1. TCOF Success Factors | 2.2 Look for Tried & Tested Options |  | Complete a pros and cons list for each option. Rate against: - Use of tried and tested methods - Likelihood of delivering goals - Modularity and scalability - Ease of building a minimum or maximum viable product Include metrics where possible | - | - | -
1. TCOF Success Factors | 3.1 Think Big, Start Small |  | Break your preferred solution into small, modular parts | Re-engage with past projects to learn new lessons about the next stage | Scale up and go big. Roll out sections / modular solution to other areas | -
1. TCOF Success Factors | 3.1 Think Big, Start Small |  | Ask the question: what is my Lego? | Validate that the solution will achieve the goals. | - | -
1. TCOF Success Factors | 3.1 Think Big, Start Small |  | Ensure people and plans are in place to develop the solution in Phase 2 | - | - | -
1. TCOF Success Factors | 3.2 Learn by Experimenting |  | Create a plan to develop an MVP or MXVP in Stage 2 | Develop module as a minimum viable product, if possible. Otherwise, develop a maximum virtual product. | Continue regular learning and reflection sessions (at least monthly) | -
1. TCOF Success Factors | 3.2 Learn by Experimenting |  | Start regular reflection sessions: weekly, fortnightly, or monthly | Continue regular learning and reflection sessions (at least monthly) | - | -
1. TCOF Success Factors | 3.3 Keep on top of risks |  | List your top five risks now | Continuously identify and mittigate risks (review at least monthly) | Continuously identify and mitigate risks (review at least monthly) | -
1. TCOF Success Factors | 3.3 Keep on top of risks |  | Create a mitigation plan for each one | - | - | -
1. TCOF Success Factors | 3.3 Keep on top of risks |  | Review and update your risk plan monthly (or more often) | - | - | -
1. TCOF Success Factors | 4.1 Adjust for optimism |  | Compare how long similar projects took in Stage 2 and 3 versus their original estimates | Look to previous projects to identify level of optimism for Stage 3, apply this contingency % to your estimate for time / cost / resources required for stage 3 | Build optimism allowances into all forecasts. | -
1. TCOF Success Factors | 4.1 Adjust for optimism |  | Adjust your forecast based on this optimism allowance and include contingency | - | - | -
1. TCOF Success Factors | 4.2 Measure What Matters, Be Ready to Step Away |  | Identify the success measures for your solution in Stage 2 | Identify the measurable success measures for your solution in Stage 3 | Confirm the built solution meets your goals. Measure this with metrics. | Record results for posterity
1. TCOF Success Factors | 4.2 Measure What Matters, Be Ready to Step Away |  | Confirm the business case do the benefits outweigh the costs? | Confirm the business case do the benefits outweigh the costs? | - | -
1. TCOF Success Factors | 4.2 Measure What Matters, Be Ready to Step Away |  | - | Confirm you've used data to validate your chosen option and plan, including optimism bias | - | -
1. TCOF Success Factors | 4.3 Be Ready to Adapt |  | Set up regular meetings with key people to adapt to a changing world | Adapt the requirements / plan / scope based as new information comes to light. | Adapt the requirements / plan / scope based as new information comes to light. | -